## Sheet1
| Cai Hong | Skyler Ganter | Joshua Patel
Sprint 1 (9/16 - 9/30) | (1)Built project framework (2)Purchase and build database for the project |  | Understand the project and set up the required software eclipse. Install additional add-ons. Complete documentation.
Sprint 2 (10/1 - 10/14) | Create SDP. | Implement Unitility methods | Create GUI. Display the relevant data from database in the GUI.
Sprint 3 (10/15 - 10/28) | (1)Built Data Access Object, implement delete,update and returnBook method. (2)JUnit Test |  | Add required interactions to the GUI i.e. book selection capability and borrow button.
Sprint 4 (10/29 - 11/11) | JUnit Test |  | Test for all cases
Final Sprint (11/12 - 11/25) | JUnit Test |  | Final review